## Iteration 1
GANTT CHART
| Team members: | Ilya - mentor; Andrew, Anastasia, Valerii - devs
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Planning
| Requirement meeting | 2020-10-01 | 1 | 2020-10-01 | 1 | 1 | 0 | All team members | 100%
| Choice of technology stack | 2020-10-01 | 1 | 2020-10-01 | 1 | 1 | 0 | All team members | 100%
| Configuration version control system | 2020-10-01 | 1 | 2020-10-01 | 1 | 1 | 0 | Ilya | 100%
| Create the roadmap (Gantt chart) | 2020-10-01 | 1 | 2020-10-08 | 8 | 8 | 0 | Andrew, Anastasia, Valerii | 100%
Design
| Design "sign up / sign in" page | 2020-10-09 | 9 | 2020-10-09 | 1 | 1 | 0 | Valerii | 100%
| Design calendar home page | 2020-10-09 | 9 | 2020-10-09 | 1 | 1 | 0 | Andrew | 100%
| Design account settings | 2020-10-09 | 9 | 2020-10-09 | 1 | 1 | 0 | Andrew | 100%
| Design wizards for calendar items | 2020-10-09 | 9 | 2020-10-09 | 1 | 1 | 0 | Valerii | 100%
| Design database | 2020-10-09 | 9 | 2020-10-10 | 2 | 2 | 0 | Anastasia | 100%
Development
| Create prototype of the project | 2020-10-12 | 12 | 2020-10-14 | 3 | 3 | 0 | Andrew, Valerii | 100%
| DB configuration/implementation | 2020-10-13 | 13 | 2020-10-14 | 2 | 2 | 0 | Anastasia | 100%
Implement the user "sign up / sign in" page
| Front-end implementation of the "sign up / sign in" page | 2020-10-15 | 15 | 2020-10-16 | 2 | 2 | 0 | Valerii | 100%
| Back-end implementation of the "sign up / sign in" page | 2020-10-16 | 16 | 2020-10-17 | 2 | 2 | 0 | Anastasia | 100%
Implement the calendar home page
| Front-end implementation of the сalendar home page | 2020-10-15 | 15 | 2020-10-17 | 3 | 3 | 0 | Andrew | 100%
Implement the calendar item: tasks
| Front-end implementation of the task wizard form | 2020-10-19 | 19 | 2020-10-20 | 2 | 0 | 2 | Anastasia | 0%
| Back-end implementation of the task | 2020-10-21 | 21 | 2020-10-22 | 2 | 0 | 2 | Anastasia | 0%
Implement the calendar item: reminders
| Front-end implementation of the reminder wizard form | 2020-10-19 | 19 | 2020-10-20 | 2 | 0 | 2 | Andrew | 0%
| Back-end implementation of the reminder | 2020-10-21 | 21 | 2020-10-22 | 2 | 0 | 2 | Andrew | 0%
Implement the calendar item: events (without connection with the other team members and attached files)
| Front-end implementation of the event wizard form | 2020-10-19 | 19 | 2020-10-20 | 2 | 0 | 2 | Valerii | 0%
| Back-end implementation of the event | 2020-10-21 | 21 | 2020-10-22 | 2 | 0 | 2 | Valerii | 0%
Implement projection of calendar items onto the calendar matrix
| Front-end implementation projection of calendar items onto the calendar matrix | 2020-10-23 | 23 | 2020-10-24 | 2 | 0 | 2 | Andrew, Anastasia | 0%
| Code review | 2020-10-26 | 26 | 2020-10-26 | 1 | 0 | 1 | Ilya | 0%
| Refactoring | 2020-10-27 | 27 | 2020-10-27 | 1 | 0 | 1 | Andrew, Anastasia, Valerii | 0%
Testing
| Create the check-list | 2020-10-02 | 2 | 2020-10-15 | 14 | 14 | 0 | Andrew, Anastasia, Valerii | 100%
| Dev-testing | 2020-10-28 | 28 | 2020-10-28 | 1 | 0 | 1 | Andrew, Valerii | 0%
| Explorary testing | 2020-10-28 | 28 | 2020-10-28 | 1 | 0 | 1 | Anastasia | 0%
| Bugfix | 2020-10-29 | 29 | 2020-10-30 | 2 | 0 | 2 | Andrew, Anastasia, Valerii | 0%
| Confirmation + Regression testing | 2020-10-31 | 31 | 2020-10-31 | 1 | 0 | 1 | Valerii, Anastasia | 0%
Risks
| risks are added to tasks and it is possible to work on weekends | [7 empty] | 0%

## Iteration 2
GANTT CHART
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Planning
| Requirement meeting | 2020-11-02 | 2 | 2020-11-02 | 1 | 0 | 1 | All team members | 0%
| Analysing and editing the roadmap (Gantt chart) | 2020-11-02 | 2 | 2020-11-02 | 1 | 0 | 1 | All team members | 0%
Development
Implement the user account settings page
| Front-end implementation of the account settings page | 2020-11-03 | 3 | 2020-11-03 | 1 | 0 | 1 | Anastasia | 0%
| Back-end implementation of the account settings page | 2020-11-04 | 4 | 2020-11-05 | 2 | 0 | 2 | Anastasia | 0%
Implementation of the calendar settings
| Front-end implementation of the сalendar settings form | 2020-11-03 | 3 | 2020-11-03 | 1 | 0 | 1 | Andrew | 0%
| Back-end implementation of calendar settings | 2020-11-04 | 4 | 2020-11-05 | 2 | 0 | 2 | Andrew | 0%
Implementation of multiple calendars management
| Front-end implementation of multiple calendars management | 2020-11-03 | 3 | 2020-11-03 | 1 | 0 | 1 | Valerii | 0%
| Back-end implementation of multiple calendars management | 2020-11-04 | 4 | 2020-11-05 | 2 | 0 | 2 | Valerii | 0%
Implementing notifications
| Implement notification in the app | 2020-11-06 | 6 | 2020-11-06 | 1 | 0 | 1 | Andrew | 0%
| Implement e-mail notification | 2020-11-07 | 7 | 2020-11-09 | 3 | 0 | 3 | Andrew | 0%
Adding other users to the event
| Front-end implementation of the adding other users to the event | 2020-11-06 | 6 | 2020-11-07 | 2 | 0 | 2 | Valerii | 0%
| Back-end implementation of the adding other users to the event | 2020-11-08 | 8 | 2020-11-09 | 2 | 0 | 2 | Valerii | 0%
Implementing uploading and downloading a file in an event
| Front-end implementation of the attached files on the event | 2020-11-06 | 6 | 2020-11-07 | 2 | 0 | 2 | Anastasia | 0%
| Back-end implementation of the attached files on the event | 2020-11-08 | 8 | 2020-11-09 | 2 | 0 | 2 | Anastasia | 0%
Implementing export of calendar and events
| Implementing export of the calendar to .ics format | 2020-11-10 | 10 | 2020-11-11 | 2 | 0 | 2 | Andrew | 0%
| Implementing export of the event to .ics format | 2020-11-11 | 11 | 2020-11-11 | 1 | 0 | 1 | Valerii, Andrew | 0%
Implementing logging and exception handling
| Implementing logging | 2020-11-10 | 10 | 2020-11-11 | 2 | 0 | 2 | Anastasia | 0%
| Implementing exception handling | 2020-11-10 | 10 | 2020-11-11 | 2 | 0 | 2 | Valerii, Anastasia | 0%
| Code review | 2020-11-12 | 12 | 2020-11-12 | 1 | 0 | 1 | Ilya | 0%
| Refactoring | 2020-11-13 | 13 | 2020-11-14 | 2 | 0 | 2 | Andrew, Anastasia, Valerii | 0%
Testing
| Dev-testing | 2020-11-15 | 15 | 2020-11-15 | 1 | 0 | 1 | Anastasia, Valerii | 0%
| Explorary testing | 2020-11-15 | 15 | 2020-11-15 | 1 | 0 | 1 | Andrew | 0%
| Bugfix | 2020-11-16 | 16 | 2020-11-18 | 3 | 0 | 3 | Andrew, Anastasia, Valerii | 0%
| Confirmation + Regression testing | 2020-11-19 | 19 | 2020-11-20 | 2 | 0 | 2 | Valerii, Andrew | 0%
Completion
| Writing technical documentation | 2020-11-21 | 21 | 2020-11-22 | 2 | 0 | 2 | Valerii | 0%
| Project presentation creation + prepearing | 2020-11-21 | 21 | 2020-11-22 | 2 | 0 | 2 | Anastasia, Andrew | 0%
Risks
risks are added to tasks and it is possible to work on weekends

## Basic Gantt Chart (hidden)
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 3 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 3 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 5 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 5 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 3 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 7 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 4 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 1 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 4 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 3 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 3 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 9 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 5 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 6 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 1 | Rachel | 0%

## Manual Chart (hidden)
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 3 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 5 | Brandon | 50% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 4 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 3 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 3 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 5 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 9 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 3 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 5 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 5 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 4 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 5 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 3 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 5 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 4 | Rachel | 40%